STATEMENT OF WORK

Website Redesign & Development

Incorporate123.co

| Prepared For: | Incorporate123 |
| --- | --- |
| Prepared By: | BIT Studios |
| Date: | February 2026 |
| Version: | 1.0 |
| Status: | Draft for Review |

# 1. Project Overview

This Statement of Work defines the scope, deliverables, timeline, and terms for the complete redesign and redevelopment of the Incorporate123.co website. The project transforms the current geography-first website into a modern, intent-first platform organized around four content pillars: Business Privacy, Asset Protection, Company Formation, and Compliance.

The approved strategy document serves as the foundational reference for all work described in this SOW.

## 1.1 Parties

Client: Incorporate123 ("Client")

Provider: BIT Studios ("Provider")

## 1.2 Project Objectives

- Reposition Incorporate123 from "Nevada incorporation company" to "Privacy, Asset Protection & Business Formation Specialists"

- Implement a pillar/cluster site architecture organized around customer intent, not geography

- Design and develop a modern, trust-building website that reflects 25 years of expertise

- Create a clear conversion flow: Education → Specifics → Comparison → Package → Conversion

- Build SEO authority in privacy and asset protection keywords where competitors have limited presence

- Restructure packages into base packages with optional add-ons to reduce decision fatigue

# 2. Scope of Work

The project encompasses a complete website redesign and redevelopment across seven phases. All work is based on the approved strategic framework including the four-pillar architecture, ~71-page site map, and intent-first positioning. The current site contains approximately 127 pages including 65+ individual Learning Center FAQ items.

## 2.1 In Scope

- Complete site architecture redesign using pillar/cluster model

- UX design including wireframes for all page types (homepage, pillar pages, cluster pages, comparison pages, package pages)

- Visual design system, high-fidelity mockups, and component library

- Content creation for all pages (~4 pillar pages, 15+ cluster pages, package pages, comparison pages, utility pages)

- SEO strategy implementation including keyword mapping, schema markup, internal linking, and meta optimization

- Full-stack WordPress development with custom theme, ACF Pro, and CMS integration for easy content management

- Responsive design for desktop, tablet, and mobile

- Google Analytics 4 and Google Search Console (both already installed) configuration verification and optimization

- QA testing, cross-browser compatibility, and performance optimization

- 301 redirect mapping from ~100+ current URLs to new structure (including Learning Center FAQ items)

- DNS configuration and launch execution

## 2.2 Out of Scope

The following items are not included in this SOW but may be added as separate engagements:

- Ongoing SEO monitoring and optimization (post-launch)

- Content marketing, blog posts, and ongoing content updates

- Paid advertising management (Google Ads, retargeting)

- Social media marketing and email campaigns

- Interactive calculators, configurators, or client portal

- Multi-language support

- Third-party integrations (CRM, accounting software)

- Hosting and ongoing maintenance (to be quoted separately)

# 3. Project Phases & Deliverables

The project is organized into seven sequential phases. Each phase concludes with client review and approval before proceeding to the next phase.

| Phase | Key Deliverables | Est. Hours | Duration |
| --- | --- | --- | --- |
| 1. Discovery & Strategy | Discovery report, finalized site architecture, content strategy, SEO keyword map, positioning framework | 28 | 1 week |
| 2. UX Design | Complete site map with URLs, user journey diagrams, wireframes for all page types, mobile/desktop layouts | 34 | 1 week |
| 3. Visual Design | Design system (colors, typography, spacing), high-fidelity mockups, component library, design specifications | 39 | 1 week |
| 4. Content Creation | All page copy (pillar, cluster, package, comparison, utility), meta descriptions, CTA copy, image alt text | 50 | 1–2 weeks |
| 5. SEO Implementation | Technical SEO audit, keyword mapping, schema markup, internal linking strategy, meta tag optimization | 19 | Concurrent |
| 6. Development | WordPress custom theme, ACF Pro integration, responsive build, contact forms, performance optimization, analytics verification | 95 | 2–3 weeks |
| 7. Testing & Launch | QA report, cross-browser verification, 301 redirects, DNS configuration, launch execution | 18–23 | 1 week |
| TOTAL |  | 283–288 | 9–12 weeks |

Development is based on WordPress with a custom theme, ACF Pro for content management, and mid-range complexity (90 base hours + 5 hours coordination). Technical stack: WordPress, HTML5, CSS3, JavaScript (ES6+), ACF Pro, Gravity Forms, WP Rocket, Cloudflare CDN. All phase estimates include project management, client coordination, and review cycle facilitation.

# 4. Project Timeline

The estimated project duration is 9–16 weeks, depending on the pace of client reviews and approval cycles. The timeline assumes reasonable response times for feedback (3–5 business days per review cycle).

| Phase | Start | End | Dependencies |
| --- | --- | --- | --- |
| Discovery & Strategy | Week 1 | Week 1 | Contract signed, GA4/GSC access shared |
| UX Design | Week 2 | Week 2 | Phase 1 approved by Client |
| Visual Design | Week 3 | Week 3 | Phase 2 approved by Client |
| Content Creation | Week 4 | Week 5 | Phase 3 approved, content inputs from Client |
| SEO Implementation | Week 4 | Week 5 | Runs concurrent with Content Creation |
| Development | Week 6 | Week 8 | Phases 3–5 approved, WordPress environment ready |
| Testing & Launch | Week 9 | Week 9 | Development complete, Client final review |

Note: Weeks 10–16 serve as buffer for extended review cycles, scope adjustments, or additional revision rounds.

# 5. Investment & Payment Terms

## 5.1 Project Investment

Pricing is based on the AI-assisted approach, which delivers approximately 47% time savings compared to traditional methods while maintaining or exceeding quality standards. All phase estimates include project management, client communication, review coordination, and meeting facilitation.

| Phase | Hours | Rate | Subtotal |
| --- | --- | --- | --- |
| Phase 1: Discovery & Strategy | 28 | $100/hr | $2,800 |
| Phase 2: UX Design | 34 | $100/hr | $3,400 |
| Phase 3: Visual Design | 39 | $100/hr | $3,900 |
| Phase 4: Content Creation | 50 | $100/hr | $5,000 |
| Phase 5: SEO Implementation | 19 | $100/hr | $1,900 |
| Phase 6: Development (WordPress) | 95 | $100/hr | $9,500 |
| Phase 7: Testing & Launch | 18–23 | $100/hr | $1,800–$2,300 |
| TOTAL | 283–288 |  | $28,300–$28,800 |

Platform: WordPress with custom theme (confirmed). Development estimate based on mid-range complexity: custom theme build, ACF Pro integration, Gravity Forms, responsive implementation, and performance optimization. Final hours may adjust slightly during Phase 1 based on feature scope refinement.

## 5.2 Payment Schedule

Payments are milestone-based, tied to phase completion and Client approval:

| Milestone | Amount | Due |
| --- | --- | --- |
| Project Kickoff | 20% of total | Upon contract signing |
| Discovery & Strategy Approved | 15% of total | Upon Phase 1 approval |
| Design Approved (UX + Visual) | 20% of total | Upon Phase 3 approval |
| Content Approved | 15% of total | Upon Phase 4 approval |
| Development Complete | 20% of total | Upon Phase 6 completion |
| Launch & Handover | 10% of total | Upon successful launch |

All invoices are payable within 15 business days of issuance.

# 6. Client Responsibilities

Timely Client participation is essential for maintaining the project timeline. The Client agrees to:

- Provide timely feedback on deliverables within 3–5 business days of submission

- Designate a single point of contact with authority to approve deliverables

- Provide access to the current website, hosting environment, and domain registrar

- Provide viewer/editor access to the existing Google Analytics 4 and Google Search Console properties for baseline data collection

- Provide any existing brand assets (logos, color preferences, fonts) and content to be preserved

- Supply subject matter expertise for content review, particularly for legal and compliance-related content

- Provide final approval at each phase gate before work proceeds to the next phase

- Make decisions on open strategic questions (package structure, domain consolidation, review platform selection)

# 7. Provider Responsibilities

BIT Studios agrees to:

- Deliver all work in accordance with the approved strategy document and this SOW

- Provide regular progress updates and maintain clear communication throughout the project

- Submit deliverables for review at each phase gate

- Incorporate reasonable Client feedback within each revision cycle (up to 2 revision rounds per phase included)

- Maintain confidentiality of all Client business information and proprietary data

- Ensure the final website meets modern web standards for performance, accessibility, and SEO

- Provide documentation for WordPress CMS usage, content editing, and site management upon handover

- Execute 301 redirects and DNS configuration for a seamless transition

# 8. Revisions & Change Orders

## 8.1 Included Revisions

Each phase includes up to two (2) rounds of revisions based on Client feedback. Revisions must be submitted in writing (email) as consolidated feedback.

## 8.2 Additional Revisions

Revision rounds beyond the included two per phase will be billed at the standard hourly rate of $100/hour. Provider will notify Client before any additional billable work begins.

## 8.3 Scope Changes

Any changes to the agreed scope of work (additional pages, features, integrations, or functionality not described in this SOW) require a written Change Order. Change Orders will include a description of the change, estimated hours, cost, and impact on timeline. Work on Change Orders will not begin until signed by both parties.

# 9. Intellectual Property & Ownership

Upon full payment, all custom work product created under this SOW — including designs, code, content, and documentation — becomes the exclusive property of the Client.

Provider retains the right to display the completed project in its portfolio and marketing materials, with Client approval.

Third-party tools, frameworks, and licensed components (e.g., WordPress core, ACF Pro, plugins, stock imagery) remain subject to their respective license terms.

# 10. Confidentiality

Both parties agree to maintain the confidentiality of proprietary business information shared during the project. This includes but is not limited to: business strategies, customer data, pricing structures, competitive intelligence, and technical specifications. Confidentiality obligations survive the termination of this agreement.

# 11. Termination

## 11.1 By Client

Client may terminate this SOW with 14 days written notice. Client is responsible for payment for all work completed through the termination date, plus any non-cancellable commitments made on Client's behalf.

## 11.2 By Provider

Provider may terminate this SOW with 14 days written notice if Client fails to fulfill responsibilities (including payment) after reasonable notice and opportunity to cure (7 business days).

## 11.3 Deliverables Upon Termination

Upon termination, Provider will deliver all completed work product to Client within 5 business days. Incomplete work will be delivered in its current state.

# 12. Warranty & Support

Provider warrants that the delivered website will function as described in this SOW for a period of 30 days following launch ("Warranty Period"). During the Warranty Period, Provider will fix any bugs or defects at no additional charge.

Post-warranty support and maintenance are available under a separate agreement.

# 13. Success Metrics

The following metrics will be used to evaluate project success, measured against baseline data collected during Phase 1:

| Metric | Target | Timeframe |
| --- | --- | --- |
| Page load speed | < 3 seconds / 90+ PageSpeed | At launch |
| Bounce rate reduction | 30% decrease | 0–3 months |
| Average time on site | 40% increase | 0–3 months |
| Organic traffic growth | 50%+ increase | 3–12 months |
| Privacy keyword rankings | Top 10 for primary terms | 6–12 months |
| Consultation requests | 35% increase | 3–6 months |
| Mobile usability score | 95+ (Google) | At launch |

# 14. Acceptance

By signing below, both parties agree to the terms and conditions outlined in this Statement of Work.

CLIENT: Incorporate123

Signature	Date

Printed Name and Title

PROVIDER: BIT Studios

Signature	Date

Printed Name and Title