## Project Task List
# | Phase | Task | Description / Details | Hours Est. | Week(s) | Dependencies | Owner | Status | Milestone
PHASE 0: PRE-PROJECT — Contract & Setup
1 | Pre-Project | Send SOW for signature | Send finalized SOW to David with signature blocks for both parties. This is the binding agreement. | — | Pre | — | Alex / BIT
2 | Pre-Project | SOW executed (both parties sign) | Obtain signatures from David (Client) and BIT Studios (Provider). Project is not officially started until signed. | — | Pre | #1 | Alex / David |  | ✓ CONTRACT
3 | Pre-Project | Invoice Milestone 1 (Discovery) | Send invoice for ~$2,520 (36 hrs × $70/hr). Due upon Discovery approval per SOW §4.2. | — | Pre | #2 | BIT Studios
4 | Pre-Project | Send Client Responsibilities checklist | Compile SOW §5 into actionable checklist for David: hosting access, GA/GSC access, brand assets, payment gateway creds, content POC designation. | — | Pre | #2 | Alex
5 | Pre-Project | Receive hosting & domain access | David provides access to current hosting environment and domain registrar. | — | Pre | #4 | David
6 | Pre-Project | Receive brand assets | David provides logos, color preferences, fonts, and any content to be preserved. | — | Pre | #4 | David
7 | Pre-Project | Install Google Analytics 4 on current site | Install fresh GA4 tracking code on live incorporate123.co to begin capturing baseline data before redesign. | 1 | Pre | #5 | Irish / Team
8 | Pre-Project | Install Google Search Console on current site | Install GSC verification and begin indexing/crawl data collection on current site. | 1 | Pre | #5 | Irish / Team
9 | Pre-Project | Set up internal project infrastructure | Create task board, time tracking, shared project folders, staging environment, communication channels. | 2 | Pre | #2 | Alex / Team
10 | Pre-Project | Brief internal team | Walk Irish and team through strategy docs, pillar/cluster architecture, client tone/expectations, and SOW scope. | 1 | Pre | #9 | Alex
11 | Pre-Project | Schedule project kickoff meeting with David | Set date for formal kickoff to begin Discovery. Confirm weekly check-in cadence. | — | Pre | #2 | Alex
PHASE 1: DISCOVERY & STRATEGY — 36 hrs · Weeks 1-2
12 | Discovery | Project kickoff meeting | Formal kickoff with David. Review goals, confirm strategy, align on communication cadence, validate assumptions from earlier conversations. | 2 | 1 | #2, #11 | Alex / David
13 | Discovery | Technical crawl of current site | Crawl all ~171 URLs with Screaming Frog or similar. Document page structure, broken links, response codes, load times, technical SEO issues. | 3 | 1 | #12 | Team
14 | Discovery | Content inventory & audit | Catalog all ~129 unique content pages. Classify each as: preserve, consolidate, rewrite, or drop. Flag the ~111 Learning Center FAQ items for consolidation. | 4 | 1 | #13 | Team
15 | Discovery | Content migration mapping | Map each of ~129 current pages to specific destination in new 71-page architecture. Identify content gaps requiring new writing. | 3 | 1 | #14 | Team
16 | Discovery | Competitive analysis (5 competitors) | Deep-dive analysis of ZenBusiness, LegalZoom, Bizee, Northwest RA, and 1 other. Analyze site structure, SEO positioning, package presentation, UX patterns. | 5 | 1 | #12 | Alex / Team
17 | Discovery | User journey mapping | Define primary conversion paths: Privacy intent → package, Asset Protection intent → package, Formation intent → package. Map decision points and CTAs. | 3 | 1 | #16 | Team
18 | Discovery | Package structure finalization | Work with David to lock down base packages, add-on structure, and pricing. Resolve which packages merge, which survive, exact add-on list. | 3 | 1-2 | #12 | Alex / David
19 | Discovery | 301 redirect mapping (draft) | Create initial mapping of all ~170 current URLs to new destinations. Edge cases flagged for resolution. | 4 | 1-2 | #15 | Team
20 | Discovery | CMS platform evaluation & recommendation | Evaluate WordPress vs. Payload CMS based on David's technical comfort, long-term maintenance, feature requirements. Present recommendation for client decision. | 3 | 2 | #12, #17 | Alex / Team
21 | Discovery | CMS platform selection (client decision) | David approves CMS platform. This locks the development approach and finalizes dev hour estimate (120-180 hrs). | — | 2 | #20 | David
22 | Discovery | Discovery report compilation | Compile all findings into comprehensive Discovery report: site audit results, content map, competitive insights, validated architecture, redirect plan, CMS recommendation. | 4 | 2 | #13-20 | Alex
23 | Discovery | Client review: Discovery report | David reviews Discovery report. Provide feedback within 3-5 business days per SOW terms. | 2 | 2 | #22 | David / Alex
24 | Discovery | Discovery approval & architecture sign-off | David formally approves Discovery report and confirms site architecture. Triggers Milestone 1 payment and UX start. | — | 2 | #23 | David |  | ✓ MILESTONE 1
PHASE 2: UX & INTERACTIVE PROTOTYPING — 53 hrs · Weeks 2-5
25 | UX & Prototype | Information architecture finalization | Finalize complete site map with all 71+ pages, URL structure, navigation hierarchy (mega menu structure, mobile nav). | 4 | 2-3 | #24 | Team
26 | UX & Prototype | User flow mapping & diagrams | Define and document primary conversion paths. Create flow diagrams for privacy→package, AP→package, formation→package journeys. | 4 | 3 | #25 | Team
27 | UX & Prototype | Prototype: Homepage | Build clickable prototype: hero section, pillar navigation blocks, direct package links, testimonial area, trust signals. Desktop + mobile. | 5 | 3 | #25, #26 | Team
28 | UX & Prototype | Prototype: Pillar pages (4) | Clickable prototypes for Privacy, Asset Protection, Formation, Compliance pillars. Progressive disclosure, cluster navigation grid, inline CTAs. | 8 | 3 | #25, #26 | Team
29 | UX & Prototype | Prototype: Package pages | Clickable prototype: 3-tier comparison grid, tooltip interactions, add-on configurator, LLC/Corp toggle, progressive disclosure. | 7 | 3-4 | #25, #18 | Team
30 | UX & Prototype | Prototype: Comparison pages | Clickable prototype: side-by-side comparison tables, decision flow, dual CTAs. Responsive mobile adaptation. | 5 | 3-4 | #25, #26 | Team
31 | UX & Prototype | Prototype: Cluster & State hub pages | Clickable prototypes: content layout, related links, cross-pillar navigation, FAQ accordion behavior. | 6 | 4 | #25, #28 | Team
32 | UX & Prototype | Prototype: Checkout flow | Multi-step clickable flow: package config → entity details → payment form → confirmation page. Mobile-optimized. | 6 | 4 | #29 | Team
33 | UX & Prototype | Prototype: Resource/FAQ pages | Clickable prototype: accordion behavior, search/filter for ~111 consolidated FAQ items. | 3 | 4 | #25 | Team
34 | UX & Prototype | Navigation & interaction patterns | Build functional mega menu, mobile nav, breadcrumbs, progressive disclosure patterns — all working in prototype. | 3 | 3-4 | #25, #27 | Team
35 | UX & Prototype | Client review: Homepage prototype | David reviews and provides feedback on homepage prototype. 3-5 business day review window. | — | 3 | #27 | David
36 | UX & Prototype | Homepage prototype approved | David signs off on homepage prototype. Triggers visual design for homepage. | — | 3-4 | #35 | David
37 | UX & Prototype | Client review: Core page prototypes | David reviews pillar, package, and comparison page prototypes. Consolidated feedback. | — | 4 | #28-30 | David
38 | UX & Prototype | Core page prototypes approved | David signs off on core templates. Triggers visual design for core pages. | — | 4 | #37 | David
39 | UX & Prototype | Iterative refinement (all prototypes) | Ongoing: daily builds, David reviews 2×/week, rapid iteration based on feedback. Spans full UX phase. | 2 | 3-5 | #27-33 | Team
PHASE 3: VISUAL DESIGN & DESIGN SYSTEM — 65 hrs · Weeks 3-5
40 | Visual Design | Design system creation | Define complete visual identity: color palette, typography scale, spacing system, button styles, form elements, icon set. | 7 | 3 | #24, #36 | Design Team
41 | Visual Design | Homepage visual design | Apply full visual treatment to approved homepage prototype. Desktop + mobile. Hero, pillar CTAs, package links, testimonials, trust signals. | 5 | 3-4 | #36, #40 | Design Team
42 | Visual Design | Client review: Homepage design | David reviews homepage visual design. Feedback within 3-5 business days. | — | 4 | #41 | David
43 | Visual Design | Homepage design approved | David signs off on homepage visual design. Triggers homepage development AND Milestone 2 payment (~$4,130). | — | 4 | #42 | David |  | ✓ MILESTONE 2
44 | Visual Design | Pillar page visual design (4) | Visual treatment for progressive disclosure patterns, cluster grid, CTAs. Desktop + mobile for all 4 pillar types. | 10 | 4 | #38, #40 | Design Team
45 | Visual Design | Package page visual design | 3-tier comparison grid styling, interactive tooltips, add-on configurator, dual CTAs, progressive disclosure. Desktop + mobile. | 8 | 4 | #38, #40 | Design Team
46 | Visual Design | Comparison page visual design | Side-by-side table styling, responsive mobile adaptation, decision-focused content blocks. | 5 | 4-5 | #38, #40 | Design Team
47 | Visual Design | Cluster page visual design | Content layout styling, FAQ accordion treatment, related links, CTA blocks. Template for 24+ pages. | 6 | 4-5 | #38, #40 | Design Team
48 | Visual Design | State hub page visual design | Cross-pillar layout, state-specific content aggregation, package quick links. | 4 | 4-5 | #38, #40 | Design Team
49 | Visual Design | Checkout flow visual design | Multi-step form styling, progress indicator, payment form design, confirmation page. Mobile-optimized. | 5 | 4-5 | #32, #40 | Design Team
50 | Visual Design | Resource/FAQ page visual design | Accordion section styling, search/filter UI, consolidated FAQ layout. | 3 | 4-5 | #33, #40 | Design Team
51 | Visual Design | Utility page visual design | Standard content layout + contact form variant with consultation booking. | 3 | 5 | #40 | Design Team
52 | Visual Design | Component library documentation | Document all reusable components: buttons, cards, forms, accordions, tooltips, CTAs — with specs for dev handoff. | 4 | 5 | #41-52 | Design Team
53 | Visual Design | Design specifications for development | Spacing, sizing, interaction specs, responsive breakpoints — everything dev needs to build accurately. | 3 | 5 | #53 | Design Team
54 | Visual Design | Client review: Core template designs | David reviews pillar, package, comparison template designs. Consolidated feedback. | — | 5 | #44-47 | David
55 | Visual Design | Core template designs approved | David signs off on core templates + first SEO specs. Triggers Milestone 3 payment (~$4,130). | — | 5 | #55 | David |  | ✓ MILESTONE 3
56 | Visual Design | Client review: Remaining designs | David reviews cluster, state hub, checkout, resource, utility designs. | — | 5 | #48-52 | David
57 | Visual Design | All designs approved | Full design sign-off. All templates ready for development. Triggers Milestone 4 payment (~$8,820) along with full SEO delivery. | — | 5 | #57, #72 | David |  | ✓ MILESTONE 4
PHASE 4: SEO STRATEGY & IMPLEMENTATION — 126 hrs · Weeks 3-8
58 | SEO | Technical SEO audit | Crawl analysis, indexation review, Core Web Vitals baseline, mobile usability, structured data gaps on current site. | 8 | 3 | #24 | SEO Team
59 | SEO | Keyword research: Privacy pillar (11 pages) | Research and map target keywords for all 11 privacy-related pages. Primary, secondary, long-tail keywords per page. | 10 | 3 | #24, #59 | SEO Team
60 | SEO | Keyword research: Asset Protection pillar (7 pages) | Research and map target keywords for all 7 AP pages. | 8 | 3-4 | #24, #59 | SEO Team
61 | SEO | Keyword research: Formation pillar (9 pages) | Research and map target keywords for all 9 formation pages. | 8 | 3-4 | #24, #59 | SEO Team
62 | SEO | Keyword research: Compliance pillar (7 pages) | Research and map target keywords for all 7 compliance pages. | 6 | 4 | #24, #59 | SEO Team
63 | SEO | Keyword research: Packages & Hubs | Research and map for 8 package pages, 4 state hubs, and utility pages. | 6 | 4 | #24, #59 | SEO Team
64 | SEO | On-page SEO specs (71 pages) | Individual spec per page: title tag, meta description, H1/H2 structure, target keywords, content guidance, word count targets. | 36 | 4-6 | #60-64 | SEO Team
65 | SEO | Schema markup strategy | Define and document schema types per template: Organization, Service, FAQ, Product, BreadcrumbList, HowTo. Implementation guide. | 8 | 5 | #65 | SEO Team
66 | SEO | Internal linking strategy | Map all pillar→cluster→comparison→package link relationships across 71+ pages. Document every link with anchor text guidance. | 8 | 5-6 | #65 | SEO Team
67 | SEO | 301 redirect mapping (final) | Finalize mapping of ~170 current URLs to new destinations. Handle edge cases, chain redirects, orphaned pages. | 8 | 5-6 | #19, #65 | SEO Team
68 | SEO | Content brief templates | Create page-type templates for David's content writing. Include SEO requirements, keyword targets, word counts, header structure per page type. | 8 | 5-6 | #65, #66 | SEO Team
69 | SEO | Deliver content briefs to David | Hand off content briefs and SEO specs to David. He begins writing ~71 pages of content per SOW §5. | — | 5-6 | #70 | Alex → David
70 | SEO | Full SEO delivery & approval | All SEO specs, schema docs, internal linking map, redirect plan, content briefs delivered. Combined with design approval for Milestone 4. | — | 6-8 | #65-71 | Alex / David
71 | SEO | Pre-launch SEO QA | Verify all specs implemented on staging: titles, metas, schema, redirects, canonicals, robots.txt, XML sitemap. | 10 | 8-9 | #65-68, Dev complete | SEO Team
72 | SEO | Post-launch monitoring setup | Configure rank tracking, crawl monitoring, index verification, GSC alerts, GA4 event tracking. | 6 | 9-10 | #73 | SEO Team
PHASE 5: DEVELOPMENT — 120-180 hrs · Weeks 4-9
73 | Development | CMS setup & configuration | Theme/project scaffold, plugin/module selection, dev environment setup, Git repo. Based on CMS decision (#21). | 8 | 4 | #21, #43 | Dev Team
74 | Development | Homepage template build | Custom build: hero with dual CTA paths, pillar navigation blocks, package links, testimonial carousel, trust signals. Responsive. | 12 | 4-5 | #43, #75 | Dev Team
75 | Development | Pillar page template build | Long-form progressive disclosure, cluster link grid, inline package CTAs, FAQ accordions, breadcrumbs, related sidebar. | 14 | 5-6 | #44, #53-54, #75 | Dev Team
76 | Development | Cluster page template build | Content layout, FAQ accordions, related cluster links, package CTA blocks, back-to-pillar nav, schema integration. | 10 | 5-6 | #48, #53-54 | Dev Team
77 | Development | Package page template build | 3-tier comparison grid, interactive tooltip system, add-on configurator with pricing, progressive disclosure, dual CTA (LLC/Corp), testimonials. | 16 | 5-7 | #45, #53-54 | Dev Team
78 | Development | Comparison page template build | Side-by-side comparison tables, responsive mobile adaptation, decision content blocks, dual package CTAs. | 8 | 6 | #46, #53-54 | Dev Team
79 | Development | State hub template build | Cross-pillar content aggregation, dynamic linking to all state-relevant pages, package quick links, state-specific FAQ. | 6 | 6-7 | #49, #53-54 | Dev Team
80 | Development | Resource/FAQ template build | Organized accordion sections, search/filter capability for ~111 consolidated FAQ items. | 6 | 6-7 | #51, #53-54 | Dev Team
81 | Development | Utility page template build | Standard content layout + contact form variant with consultation booking CTA. | 4 | 7 | #52, #53-54 | Dev Team
82 | Development | Checkout flow build | Multi-step: package configuration, entity details form, LLC/Corp selection with price adjust, mobile-optimized form design. | 14 | 6-8 | #50, #53-54 | Dev Team
83 | Development | Payment integration (Stripe/PayPal) | Stripe and/or PayPal setup, test transactions, order confirmation emails (client + admin), basic order tracking in CMS admin. | 10 | 7-8 | #84 | Dev Team
84 | Development | Responsive implementation (all templates) | Mobile optimization for all 9 template types + checkout. Test on iOS Safari, Android Chrome. | 10 | 7-8 | #76-84 | Dev Team
85 | Development | Content entry (~71 pages) | Enter David-supplied content into CMS for all pages. Format per design specs and SEO requirements. | 12 | 7-9 | #71, David content | Dev Team
86 | Development | Schema markup implementation | Implement schema types per SEO specs: Organization, Service, FAQ, Product, BreadcrumbList, HowTo. | 6 | 8 | #66, #76-83 | Dev Team
87 | Development | 301 redirect implementation | Implement all ~170 redirects per final redirect map. Server-level or plugin-based depending on CMS. | 6 | 8-9 | #68 | Dev Team
88 | Development | Performance optimization | Image optimization, caching setup, lazy loading, Core Web Vitals optimization. Target: 90+ PageSpeed score. | 6 | 8-9 | #76-83 | Dev Team
89 | Development | Analytics & tracking setup | GA4 configuration on new site, GSC verification, event tracking for conversions, form submissions, package selections. | 4 | 8-9 | #76 | Dev Team
90 | Development | Internal linking implementation | Implement all pillar→cluster→comparison→package links per SEO internal linking map. | 4 | 8-9 | #67, #87 | Dev Team
91 | Development | Staging site ready for review | All templates built, content entered, checkout working, redirects in place. Full site on staging URL. | — | 9 | #75-92 | Dev Team |  | ✓ MILESTONE 5
PHASE 6: TESTING & LAUNCH — 36 hrs · Weeks 8-10
92 | Testing & Launch | Cross-browser testing | Test all templates + checkout in Chrome, Safari, Firefox, Edge. Document and fix issues. | 4 | 8-9 | #93 | QA / Dev
93 | Testing & Launch | Mobile device testing | Test on iOS Safari, Android Chrome — all templates + checkout. Responsive verification. | 4 | 8-9 | #93 | QA / Dev
94 | Testing & Launch | Checkout & payment testing | End-to-end order flow with Stripe/PayPal test transactions. Verify order emails, admin notifications, edge cases. | 4 | 8-9 | #85, #93 | QA / Dev
95 | Testing & Launch | Content QA | Verify all ~71 pages: content accuracy, links working, images loading, formatting correct, no placeholder text. | 4 | 9 | #87, #93 | QA / Team
96 | Testing & Launch | 301 redirect verification | Test every one of ~170 redirects. Verify no chains, no loops, all resolve correctly. | 3 | 9 | #89 | QA / SEO
97 | Testing & Launch | Performance verification | Core Web Vitals pass, PageSpeed 90+ target, <3 second load times. Fix any issues. | 3 | 9 | #90 | QA / Dev
98 | Testing & Launch | SEO pre-launch QA | Coordinate with SEO team: verify titles, metas, schema, robots.txt, XML sitemap, canonicals on staging. | 4 | 9 | #73 | SEO / QA
99 | Testing & Launch | Client staging walkthrough | David walks through complete staging site. Reviews all pages, checkout, mobile. Provides final feedback. | — | 9 | #94-100 | David / Alex
100 | Testing & Launch | Bug fixes from client review | Address all issues identified during David's staging walkthrough. | 4 | 9-10 | #101 | Dev Team
101 | Testing & Launch | Final client approval for launch | David gives written go-ahead to launch. Last gate before go-live. | — | 10 | #102 | David
102 | Testing & Launch | DNS configuration & go-live | DNS switch, SSL certificate verification, immediate smoke testing of live site. | 3 | 10 | #103 | Dev Team
103 | Testing & Launch | Post-launch smoke testing | Verify all pages live, checkout working, redirects firing, analytics tracking, no broken links. | 3 | 10 | #104 | QA / Dev
104 | Testing & Launch | Site live & launch confirmed | Site is live, redirects verified, analytics confirmed. Triggers Milestone 6 payment (~$2,520). | — | 10 | #105 | Alex / David |  | ✓ MILESTONE 6
PHASE 7: POST-LAUNCH — Weeks 10-12+
105 | Post-Launch | Post-launch monitoring (Week 1) | Monitor analytics, redirect performance, search rankings, crawl errors, user behavior. Fix any issues. | 8 | 10-11 | #106 | Team / SEO
106 | Post-Launch | Post-launch monitoring (Week 2) | Continue monitoring. Verify Google indexing of new pages, rankings stabilizing, no traffic drops. | 6 | 11-12 | #107 | Team / SEO
107 | Post-Launch | CMS training & documentation handoff | Provide David with CMS usage docs and walkthrough for content editing, page updates, and site management. | 4 | 10-11 | #106 | Alex / Dev
108 | Post-Launch | Post-launch SEO monitoring config | Rank tracking active, crawl monitoring running, GSC alerts configured, GA4 dashboards set up. | — | 10-11 | #74 | SEO Team
109 | Post-Launch | 30-day warranty period begins | Per SOW §11: BIT Studios fixes any bugs or defects at no additional charge for 30 days post-launch. | — | 10+ | #106 | BIT Studios
110 | Post-Launch | Project closeout | Final deliverable handoff, all logins/credentials transferred, project retrospective, discuss ongoing maintenance options. | 2 | 12+ | #107-111 | Alex / David

## Summary
Workstream | Hours | Rate | Subtotal | Weeks
Discovery & Strategy | 36 | $70/hr | $2,520 | 1-2
UX & Design (parallel tracks) | 118 | $70/hr | $8,260 | 2-5
SEO Strategy & Implementation | 126 | $70/hr | $8,820 | 3-8
Development (CMS TBD) | 120-180 | $70/hr | $8,400-$12,600 | 4-9
Testing & Launch | 36 | $70/hr | $2,520 | 8-10
TOTAL PROJECT | 316 + 120-180 dev |  | $30,520-$34,720 | ~10 weeks

## Payment Milestones
# | Milestone | What's Delivered | Approx. Amount | Due
1 | Kickoff | Discovery complete, architecture confirmed | ~$2,520 | Upon Discovery approval
2 | Homepage Approved | Homepage prototype + visual design signed off | ~$4,130 | Upon homepage approval
3 | Core Templates Approved | Pillar, Package, Comparison templates + first SEO specs | ~$4,130 | Upon core template approval
4 | Full Design + SEO | All templates signed off, all SEO specs delivered | ~$8,820 | Upon full design + SEO delivery
5 | Development | CMS build complete, staging ready | $8,400-$12,600 | Upon dev completion
6 | Launch | Testing, QA, go-live, monitoring | ~$2,520 | Upon successful launch