SCOPE OF WORK

Incorporate123.co

Website Redesign & Redevelopment

Internal Review — Deliverables & Effort

Prepared by: BIT Studios

Prepared for: Incorporate123

February 2026

Scope at a Glance 71+ pages across 8–10 custom CMS templates 4 content pillars with 24 cluster pages, 6 comparison pages, 8 package pages 170 URL redirects mapped from current site to new architecture 71 individual SEO specs with keyword targeting, schema markup, and internal linking Full e-commerce checkout with package configuration, Stripe/PayPal integration Complete content migration preserving 25 years of domain authority CMS platform flexibility — WordPress or Payload CMS, selected after Discovery and Design

Supporting Documents Two visual companions to this scope are available online. Both use the same password. Project Scope Overview — Visual walkthrough of what we’re building, effort per workstream, and how the timeline overlaps. Start here for the big picture. https://www.bitstudios.com/incorporate123-project-scope-overview/ Site Strategy & Architecture — The strategic foundation: site organization, visitor flow, and pillar/cluster model. Refer back to this when reviewing structure decisions. https://www.bitstudios.com/incorporate123-co/ Password: Inc123 These documents and this scope describe the same project. Use whichever format is easier for your review.

# 1. Project Overview

This Statement of Work defines the scope, deliverables, timeline, and terms for the complete redesign and redevelopment of the Incorporate123.co website. The project transforms the current geography-first website into a modern, intent-first platform organized around four content pillars: Business Privacy, Asset Protection, Company Formation, and Compliance.

The approved strategy document serves as the foundational reference for all work described in this SOW.

Target Audience: Small business owners and entrepreneurs with $500k+ in assets who prioritize privacy and asset protection over lowest price.

## 1.1 Parties

Client: Incorporate123 (“Client”)

Provider: BIT Studios (“Provider”)

## 1.2 Project Objectives

- Reposition Incorporate123 from “Nevada incorporation company” to “Privacy, Asset Protection & Business Formation Specialists”

- Implement a pillar/cluster site architecture organized around customer intent, not geography

- Design and develop a modern, trust-building website that reflects 25 years of expertise

- Create a clear conversion flow: Education → Specifics → Comparison → Package → Conversion

- Build SEO authority in privacy and asset protection keywords where competitors have limited presence

- Restructure packages into base packages with optional add-ons to reduce decision fatigue

# 2. Scope of Work

The project encompasses a complete website redesign and redevelopment across five overlapping workstreams. All work is based on the approved strategic framework including the four-pillar architecture, ~71-page site map, and intent-first positioning. The CMS platform (WordPress or Payload CMS) will be determined after Discovery and UX & Design, and agreed upon with the Client.

## 2.1 Current Site Inventory

The current site contains approximately 171 URLs across 15 template types. Key metrics:

| Metric | Count | Notes |
| --- | --- | --- |
| Total current URLs | ~171 | Including all paths and duplicates |
| Unique content pages | ~129 | After removing ~42 duplicate FAQ URLs |
| Current template types | 15 | Many serve only 1–3 pages |
| Learning Center FAQ items | ~111 | Across overlapping category paths |
| New site pages (target) | ~71 | Across 8–10 custom templates |
| 301 redirects required | ~170 | Every current URL mapped to new structure |

Why 129 pages becomes 71 No content is being lost. The current site’s ~129 unique pages include significant duplication and fragmentation — the Learning Center alone has ~111 FAQ items, many appearing under multiple overlapping category URLs. Thin pages that serve only a handful of visitors sit alongside redundant service descriptions that cover the same ground from different angles. The new 71-page architecture consolidates all of that into focused, authoritative pages. FAQ content moves into contextual sections on pillar, cluster, and package pages rather than living as standalone URLs. Overlapping service pages merge into single pages that carry more weight with search engines. Every piece of content worth preserving is mapped to a specific destination in the new structure, and ~170 redirects ensure no traffic or search authority is lost in the transition.

## 2.2 New Site Architecture — Complete Page Inventory

The redesigned site is organized around four content pillars based on customer intent. Below is the complete page-by-page inventory:

Pillar 1: Business Privacy (Lead Pillar) — /privacy/

This is the primary pillar. Most prospects arrive searching for privacy solutions. 10 pages.

| Page | Type | URL | Purpose |
| --- | --- | --- | --- |
| Business Privacy | Pillar | /privacy/ | Main education hub — why privacy matters |
| Anonymous LLC | Cluster | /anonymous-llc/ | How to form an LLC with no public record |
| Anonymous Corporation | Cluster | /anonymous-corporation/ | Corporate privacy structures |
| Nominee Services | Cluster | /nominee-services/ | Year-round nominees vs competitor “for a day” |
| Wyoming Privacy | Cluster | /wyoming-privacy/ | WY-specific privacy advantages |
| Nevada Privacy | Cluster | /nevada-privacy/ | NV-specific privacy advantages |
| California Private Inc. | Cluster | /california-private-incorporation/ | WY formation + CA foreign registration |
| Florida Private Inc. | Cluster | /florida-private-incorporation/ | WY formation + FL foreign registration |
| BOI Reporting | Cluster | /beneficial-ownership-reporting/ | Reporting requirements and privacy impact |
| Best State for Privacy | Comparison | /best-state-for-privacy/ | Multi-state comparison for privacy |
| WY vs NV for Privacy | Comparison | /wyoming-vs-nevada-privacy/ | Head-to-head privacy comparison |

Pillar 2: Asset Protection — /asset-protection/

Educates on the difference between privacy and asset protection. 7 pages.

| Page | Type | URL | Purpose |
| --- | --- | --- | --- |
| Asset Protection | Pillar | /asset-protection/ | Main education hub — why AP matters |
| Nevada Asset Protection | Cluster | /nevada-asset-protection/ | NV-specific AP laws and structures |
| Wyoming Asset Protection | Cluster | /wyoming-asset-protection/ | WY-specific AP advantages |
| Investment Holding LLC | Cluster | /investment-holding-llc/ | Holding structures for investors |
| Charging Order Protection | Cluster | /charging-order-protection/ | Single-member LLC protections |
| Best State for AP | Comparison | /best-state-for-asset-protection/ | Multi-state AP comparison |
| WY vs NV for AP | Comparison | /wyoming-vs-nevada-asset-protection/ | Head-to-head AP comparison |

Pillar 3: Company Formation — /formation/

Core formation education and state guidance. 9 pages.

| Page | Type | URL | Purpose |
| --- | --- | --- | --- |
| Company Formation | Pillar | /formation/ | Main education hub — entity selection |
| Wyoming LLC | Cluster | /wyoming-llc/ | WY LLC formation details |
| Wyoming Corporation | Cluster | /wyoming-corporation/ | WY Corp formation details |
| Nevada LLC | Cluster | /nevada-llc/ | NV LLC formation details |
| Nevada Corporation | Cluster | /nevada-corporation/ | NV Corp formation details |
| Shelf Companies | Cluster | /shelf-companies/ | Aged entity options and benefits |
| LLC vs Corporation | Cluster | /llc-vs-corporation/ | Entity type comparison |
| Wyoming vs Nevada | Comparison | /wyoming-vs-nevada/ | State-level formation comparison |
| Shelf vs New Formation | Comparison | /shelf-company-vs-new-formation/ | Formation approach comparison |

Pillar 4: Compliance — /compliance/

Post-formation support and ongoing compliance. 7 pages.

| Page | Type | URL | Purpose |
| --- | --- | --- | --- |
| Compliance | Pillar | /compliance/ | Main hub — minimum necessary compliance |
| Registered Agent Services | Cluster | /registered-agent/ | What RA services include |
| Wyoming Registered Agent | Cluster | /wyoming-registered-agent/ | WY-specific RA information |
| Nevada Registered Agent | Cluster | /nevada-registered-agent/ | NV-specific RA information |
| Annual Reports | Cluster | /annual-reports/ | Reporting requirements by state |
| Foreign State Registration | Cluster | /foreign-state-registration/ | Operating in your home state |
| Domestication | Cluster | /domestication/ | Moving existing entities to WY/NV |

Package Pages (Conversion Endpoints)

All pillar and cluster content funnels to these pages. 8 pages.

| Package | URL | Includes |
| --- | --- | --- |
| Wyoming Gold (with Privacy) | /wyoming-private-incorporation/ | 3-tier pricing, add-ons, progressive disclosure, FAQ |
| Wyoming Silver (no Privacy) | /wyoming-incorporation/ | 3-tier pricing, add-ons, progressive disclosure, FAQ |
| Nevada Gold (with Privacy) | /nevada-private-incorporation/ | 3-tier pricing, add-ons, progressive disclosure, FAQ |
| Nevada Silver (no Privacy) | /nevada-incorporation/ | 3-tier pricing, add-ons, progressive disclosure, FAQ |
| Nevada Bronze (basic) | /nevada-basic-incorporation/ | Simplified pricing, add-ons, FAQ |
| California Private | /california-private-incorporation/ | WY formation + CA registration package |
| Florida Private | /florida-private-incorporation/ | WY formation + FL registration package |
| Shelf Companies | /shelf-companies/ | Aged entity inventory and pricing |

State Hub Pages

Cross-pillar landing pages for geographic searches. 4 pages.

| Hub | URL | Links To |
| --- | --- | --- |
| Wyoming | /wyoming/ | WY LLC, Corp, Privacy, Asset Protection, RA, Packages |
| Nevada | /nevada/ | NV LLC, Corp, Privacy, Asset Protection, RA, Packages, Shelf |
| California | /california/ | CA Private Incorporation, Compliance |
| Florida | /florida/ | FL Private Incorporation, Compliance |

Utility & Support Pages

Standard pages plus offshore content (de-emphasized). 9+ pages.

| Page | URL | Notes |
| --- | --- | --- |
| Homepage | / | Hero, pillar CTAs, direct package links, testimonials, trust signals |
| About Us | /about/ | 25-year history, team, expertise |
| Contact | /contact/ | Contact form, phone, consultation CTA |
| FAQ | /faq/ | Consolidated from ~111 Learning Center items |
| Blog | /blog/ | Ongoing content marketing |
| Testimonials | /testimonials/ | Client stories and social proof |
| Client Login | /login/ | Existing client portal access |
| Privacy Policy | /privacy-policy/ | Legal compliance |
| Terms of Service | /terms/ | Legal compliance |
| Offshore (de-emphasized) | /offshore/ | Retained for SEO authority, not in main nav |

Total Page Count Summary 4 Pillar Pages + 24 Cluster Pages + 6 Comparison Pages + 8 Package Pages + 4 State Hubs + 9+ Utility Pages = 55–71+ unique pages Each page requires: UX prototyping, visual design, SEO specification, CMS template implementation, content integration, QA testing, and redirect mapping.

## 2.3 Custom CMS Templates — Detailed Complexity

Each template is a custom design with unique interaction patterns, not simple content pages. The CMS platform (WordPress or Payload CMS) will be selected after Discovery and Design:

| Template | Pages Using | Key Components & Complexity |
| --- | --- | --- |
| Homepage | 1 | Hero with dual CTA paths, 3 pillar navigation blocks, secondary direct-to-package CTAs, testimonial carousel, trust signals section, responsive mobile layout |
| Pillar Page | 4 | Long-form educational content with progressive disclosure, cluster link grid, inline package CTAs, FAQ accordions, breadcrumb navigation, related content sidebar |
| Cluster Page | 24+ | Focused topic content, FAQ accordions, related cluster links, package CTA blocks, back-to-pillar navigation, schema markup integration |
| Package Detail | 8–10 | 3-tier pricing comparison grid, interactive tooltip system, optional add-on configurator with pricing, progressive disclosure (scanner vs. reader), dual CTA (LLC/Corp), testimonials, FAQ section |
| Comparison Page | 6 | Side-by-side comparison tables, decision-focused content blocks, dual package CTAs, responsive table design for mobile |
| State Hub | 4 | Cross-pillar content aggregation, dynamic linking to all state-relevant pages, package quick links, state-specific FAQ |
| Resource/FAQ | 5–10 | Organized accordion sections, search/filter capability, consolidated from ~111 current Learning Center items |
| Checkout Flow | 3–4 | Multi-step process: package configuration, entity details form, payment integration (Stripe/PayPal), order confirmation, email receipts, mobile-optimized form design |
| Utility Page | 5–7 | Standard content layout, contact form variant with consultation booking |

## 2.4 Package Selection & Checkout Flow

The redesigned site replaces the current checkout process with a streamlined package selection and checkout flow:

- Package selection page with tier comparison (Basic/Executive/MAX)

- Add-on configuration (Foreign Registration, Domestication, Virtual Office upgrades)

- Entity type selection (LLC vs. Corporation) with price adjustment

- Checkout form with client details and entity information fields

- Payment gateway integration (Stripe and/or PayPal)

- Order confirmation emails (client notification + admin notification)

- Basic order tracking in CMS admin dashboard

- Mobile-responsive checkout optimized for conversion

## 2.5 Complete Scope Summary

| Category | Deliverables | Volume |
| --- | --- | --- |
| Site Architecture | Pillar/cluster model, URL structure, internal linking map, navigation design | 71+ pages mapped |
| UX & Design (Parallel Tracks) | Clickable prototype pages showing the full flow and workings of the site, plus visual design applied to each section as it’s approved — design system, component library, dev-ready specs | 10–20 prototype pages 16+ visual designs + system |
| SEO Strategy | Technical audit, keyword mapping per page, on-page specs, schema markup, internal linking strategy | 71 individual page specs |
| Content Migration | Map ~129 current pages to new structure, consolidate ~111 FAQ items, preserve content | 129 pages audited |
| 301 Redirects | Map every current URL to new destination, implement redirects, verify post-launch | ~170 redirects |
| CMS Development | Custom theme, 9 template types, checkout flow, payment integration, responsive build | Full custom build |
| Package Pages | 3-tier comparison, tooltip system, add-on config, progressive disclosure, dual CTAs | 8 interactive pages |
| Testing & QA | Cross-browser, mobile, checkout/payment, redirect verification, performance, analytics | All 71+ pages |
| Post-Launch | 1–2 weeks monitoring, analytics verification, SEO monitoring, bug fixes | Full site monitoring |

## 2.6 Out of Scope

The following items are not included in this SOW but may be added as separate engagements:

- Page copywriting and content creation (Client-supplied, using our SEO specs and content briefs)

- Content marketing, blog posts, and ongoing content updates

- Ongoing SEO monitoring and optimization (post-launch)

- Paid advertising management (Google Ads, retargeting)

- Social media marketing and email campaigns

- Interactive calculators, configurators, or client portal

- Multi-language support

- Third-party integrations (CRM, accounting software)

- Hosting and ongoing maintenance (to be quoted separately)

# 3. How the Project Works

This project runs as five overlapping workstreams, not a sequence of steps you wait between. As each major section of the site gets your approval, the next team picks it up immediately. That means development on the homepage can begin while other pages are still being designed, and SEO specifications are written as templates are confirmed.

For a visual overview of the timeline, workstreams, and deliverable counts, see the Project Scope Overview at bitstudios.com/incorporate123-project-scope-overview (password: Inc123).

You Approve as We Go Each major section of the site follows its own cycle: Prototype → Your Sign-off → Visual Design → Your Sign-off → Development Begins. Different sections move at different speeds, so the homepage can be in development while package pages are still in design.

## 3.1 Overlapping Timeline

The project is estimated at 10 weeks, with workstreams overlapping to keep things moving. The timeline assumes feedback within 3–5 business days per review.

| Workstream | Weeks | Notes |
| --- | --- | --- |
| Discovery & Strategy | 1–2 | Sets the foundation; everything else depends on this |
| UX & Design | 2–5 | Starts as soon as architecture is confirmed. Parallel tracks: prototype + visual design |
| SEO | 3–8 | Starts as soon as site structure is locked. Specs roll out section by section |
| Development | 4–9 | Starts as soon as the first approved designs are ready |
| Testing & Launch | 8–10 | Ramps up as development is completed; full QA before go-live |

Note: Additional weeks serve as buffer for extended review cycles, scope adjustments, or additional revision rounds.

## 3.2 Discovery & Strategy

36 hours · Weeks 1–2

| Task | Description |
| --- | --- |
| Current site audit | Crawl and inventory all ~171 URLs, identify content to preserve vs. consolidate |
| Content mapping | Map ~129 unique pages to new 71-page architecture, identify gaps and redundancies |
| Competitive analysis | Analyze top 5 competitors’ site structure, SEO positioning, package presentation |
| User journey mapping | Define primary user paths for privacy, asset protection, and formation intents |
| Discovery report | Compile findings, strategic recommendations, and validated architecture |
| Redirect planning | Create initial mapping of ~170 current URLs to new destinations |
| Stakeholder alignment | Client meetings, strategy review, approval process |

Deliverables: Discovery report, finalized site architecture, content migration map, redirect plan draft, positioning framework

✓ Milestone: Site architecture confirmed, you approve → UX & Design begins

## 3.3 UX, Prototyping & Design

These two tracks run side by side. As each section’s prototype is approved, visual design begins on that section immediately. Daily updates, your review twice per week. By the end of this workstream, you will be clicking through a fully designed, interactive representation of your new site.

UX & Interactive Prototyping — 53 hours

Rapid, iterative build of 10–20 clickable prototype pages. You click through the actual site experience—navigation, page flows, progressive disclosure, checkout steps, package comparison—before and during visual design.

| Task | Description |
| --- | --- |
| Information architecture | Finalize site map with all 71+ pages, URL structure, and navigation hierarchy |
| User flow mapping | Define and prototype primary conversion paths: privacy → package, asset protection → package, formation → package |
| Prototype — Homepage | Clickable prototype: hero, pillar navigation, package links, trust signals |
| Prototype — Pillar pages | Clickable prototype: progressive disclosure, cluster navigation, inline CTAs |
| Prototype — Package pages | Clickable prototype: 3-tier comparison, tooltip interactions, add-on configurator, LLC/Corp toggle |
| Prototype — Comparison pages | Clickable prototype: side-by-side tables, decision flow, dual CTAs |
| Prototype — Cluster & State hubs | Clickable prototype: content layout, related links, cross-pillar navigation |
| Prototype — Checkout flow | Multi-step clickable flow: package config → entity details → payment → confirmation |
| Prototype — Resource/FAQ | Clickable prototype: accordion behavior, search/filter interaction |
| Navigation & interaction patterns | Mega menu, mobile nav, breadcrumbs, progressive disclosure—all functional in prototype |
| Iterative refinement | Daily builds, your reviews 2×/week, rapid iteration based on feedback |

Visual Design & Design System — 65 hours (overlapping)

As each section’s prototype is approved, the visual identity—brand, typography, color, and polish—is applied immediately. The interaction patterns are proven; this step makes them look as good as they work.

| Task | Description |
| --- | --- |
| Design system creation | Color palette, typography scale, spacing system, button styles, form elements, icon set |
| Homepage design | Full visual design applied to validated prototype, desktop + mobile |
| Pillar page design | Visual treatment for progressive disclosure patterns, cluster grid, CTAs |
| Cluster page design | Content layout styling, FAQ accordion treatment, CTA blocks |
| Package page design | Visual design for 3-tier comparison grid, tooltips, configurator, dual CTAs |
| Comparison page design | Side-by-side table styling, responsive mobile adaptation |
| State hub design | Cross-pillar layout, state-specific content aggregation styling |
| Checkout flow design | Multi-step form styling, progress indicator, payment form, confirmation |
| Component library | Document all reusable components: buttons, cards, forms, accordions, tooltips, CTAs |
| Design specifications | Spacing, sizing, and interaction specs for development handoff |
| Client review | Per-template review and feedback incorporation |

Deliverables: 10–20 interactive prototype pages, complete design system, high-fidelity visual designs for all template types (desktop + mobile), component library, design specifications for development handoff

✓ You approve as we go: Homepage approved → Homepage build starts · Core pages approved → Build continues · All pages approved → Full build

## 3.4 SEO Strategy & Implementation

126 hours · Weeks 3–8

This is the largest single workstream because every page on the site requires individual SEO specification. This is not templated work—each of the 71+ pages gets custom keyword targeting, meta descriptions, schema markup, and internal linking instructions. SEO work starts as soon as the site structure is locked and rolls out section by section as pages are confirmed.

| Task | Description |
| --- | --- |
| Technical SEO audit | Crawl analysis, indexation review, Core Web Vitals, mobile usability, structured data gaps |
| Keyword research — Privacy pillar | Research and map target keywords for all 11 privacy-related pages |
| Keyword research — Asset Protection | Research and map target keywords for all 7 AP pages |
| Keyword research — Formation pillar | Research and map target keywords for all 9 formation pages |
| Keyword research — Compliance pillar | Research and map target keywords for all 7 compliance pages |
| Keyword research — Packages & Hubs | Research and map for 8 package pages, 4 state hubs, utility pages |
| On-page SEO specs (71 pages) | Individual specs per page: title tag, meta description, H1/H2 structure, target keywords, content guidance |
| Schema markup strategy | Define and document schema types for each template: Organization, Service, FAQ, Product, BreadcrumbList, HowTo |
| Internal linking strategy | Map all pillar → cluster → comparison → package link relationships across 71+ pages |
| 301 redirect mapping | Finalize mapping of ~170 current URLs to new destinations, handle edge cases |
| Content brief templates | Create templates for Client content writing with SEO requirements per page type |
| Pre-launch SEO QA | Verify all specs implemented on staging: titles, metas, schema, redirects, canonicals, robots |
| Post-launch monitoring setup | Configure rank tracking, crawl monitoring, index verification, GSC alerts |

Why 126 hours for SEO? Consider: 71 pages × ~30 minutes per on-page spec alone = 35.5 hours. Add keyword research across 4 distinct pillar topics, schema markup for 9 template types, internal linking strategy connecting 46+ content relationships, redirect mapping for 170 URLs, technical audit, content briefs, pre-launch QA, and monitoring setup. At 126 hours, this workstream is efficiently scoped for the volume of work.

Deliverables: Technical SEO audit report, keyword mapping for all 71+ pages, on-page SEO specifications per page, schema markup documentation, internal linking map, 301 redirect plan (~170 URLs), content brief templates, pre-launch QA report, post-launch monitoring configuration

## 3.5 Development (WordPress or Payload CMS)

120–180 hours* · Weeks 4–9

*Development hours to be confirmed after Discovery, based on final feature scope, complexity, and CMS platform selection. The CMS (WordPress or Payload CMS) will be selected collaboratively and agreed upon with the Client. Development starts as approved designs are ready—homepage build begins while other pages are still being designed.

| Task | Description |
| --- | --- |
| CMS setup & configuration | Theme/project scaffold, plugin/module selection, development environment |
| Homepage template | Custom build with hero, pillar CTAs, package links, testimonials, trust signals |
| Pillar page template | Long-form with progressive disclosure, cluster grid, inline CTAs |
| Cluster page template | Content layout, FAQ accordion, related links, package CTAs |
| Package page template | 3-tier comparison, tooltip system, add-on configurator, progressive disclosure, dual CTAs |
| Comparison page template | Side-by-side tables, responsive mobile adaptation, dual CTAs |
| State hub template | Cross-pillar aggregation, dynamic linking |
| Resource/FAQ template | Accordion system, search/filter for ~111 items |
| Utility page template | Standard content + contact form variant |
| Checkout flow | Multi-step: package config, entity details, payment form, confirmation |
| Payment integration | Stripe and/or PayPal setup, testing, order emails |
| Responsive implementation | Mobile optimization for all 9 templates + checkout |
| Content entry | Enter Client-supplied content for all ~71 pages |
| Performance optimization | Image optimization, caching, lazy loading, Core Web Vitals |
| Analytics & tracking | GA4 verification, GSC configuration, event tracking |

Development Estimate: 120–180 hours Final scope confirmed after Discovery and CMS platform selection (WordPress or Payload CMS). The package page template alone—with its 3-tier comparison grid, interactive tooltip system, add-on configurator, and progressive disclosure—represents more complexity than many entire small-business websites.

✓ Milestone: Core pages working on staging → You walk through the full site

## 3.6 Testing & Launch

36 hours · Weeks 8–10

| Task | Description |
| --- | --- |
| Cross-browser testing | Chrome, Safari, Firefox, Edge — all templates + checkout |
| Mobile testing | iOS Safari, Android Chrome — all templates + checkout |
| Checkout & payment testing | End-to-end order flow with Stripe/PayPal test transactions |
| 301 redirect implementation | Implement all ~170 redirects, verify each one |
| Content QA | Verify all ~71 pages: content accuracy, links, images, formatting |
| Performance verification | Core Web Vitals, page speed, mobile performance |
| SEO pre-launch checklist | Coordinated with SEO workstream: verify titles, metas, schema, robots, sitemap |
| Staging client review | Your walkthrough of the complete staging site |
| Launch execution | DNS, go-live, immediate smoke testing |
| Post-launch monitoring | 1–2 weeks: analytics, redirects, rankings, bug fixes, performance |

✓ Milestone: Site live, redirects verified, monitoring active

# 4. Effort Estimate

All workstream estimates include project management, communication, review coordination, and meeting facilitation.

| Workstream | Hours | Notes |
| --- | --- | --- |
| Discovery & Strategy | 36 | Weeks 1–2 |
| UX & Interactive Prototyping | 53 | Weeks 2–5 (parallel with Visual Design) |
| Visual Design & Design System | 65 | Weeks 2–5 (parallel with Prototyping) |
| SEO Strategy & Implementation | 126 | Weeks 3–8 |
| Development (WordPress or Payload CMS) | 120–180* | Weeks 4–9 |
| Testing & Launch | 36 | Weeks 8–10 |

Total Effort: 436–496 hours Non-development workstreams: 316 hours Development estimate: 120–180 hours *Development hours finalized after Discovery and CMS platform selection.

## 4.1 Milestone Checkpoints

Work is approved in rolling milestones, not all-at-once:

| Milestone | What’s Delivered |
| --- | --- |
| 1. Discovery Complete | Finalized site architecture, content migration map, redirect plan |
| 2. Homepage Approved | Homepage prototype + visual design signed off |
| 3. Core Templates Approved | Pillar, Package, Comparison templates signed off + first SEO specs |
| 4. Full Design + SEO | All templates signed off, all SEO specs delivered |
| 5. Development Complete | CMS build complete, staging ready for walkthrough |
| 6. Launch | Testing, QA, go-live, post-launch monitoring active |

# 5. Client Responsibilities

Timely Client participation is essential for maintaining the project timeline. The Client agrees to:

- Provide timely feedback on deliverables within 3–5 business days of submission

- Designate a single point of contact with authority to approve deliverables

- Provide access to the current website, hosting environment, and domain registrar

- Provide viewer/editor access to existing Google Analytics 4 and Google Search Console properties

- Provide any existing brand assets (logos, color preferences, fonts) and content to be preserved

- Produce all page content (copywriting) for the ~71 site pages, using the SEO specifications, page-type templates, and content briefs provided by Provider

- Supply subject matter expertise for content review, particularly for legal and compliance-related content

- Approve each major section’s prototype and design before development begins on that section

- Make decisions on open strategic questions (package structure, domain consolidation, review platform selection)

- Provide payment gateway credentials and merchant account details for checkout setup

Delays in Client-supplied content or feedback beyond the agreed 3–5 business day window may extend the project timeline.

# 6. Provider Responsibilities

BIT Studios agrees to:

- Deliver all work in accordance with the approved strategy document and this scope

- Provide regular progress updates and maintain clear communication throughout the project

- Submit deliverables for review at each milestone

- Incorporate reasonable Client feedback within each revision cycle (up to 2 revision rounds per workstream included)

- Ensure the final website meets modern web standards for performance, accessibility, and SEO

- Provide documentation for CMS usage and site management upon handover

- Execute 301 redirects for a seamless transition