INCORPORATE123 WEBSITE REDESIGN

Internal Alignment

Questions & Decisions for Jeff

Prepared by Alex  ·  BIT Studios  ·  February 2026  ·  INTERNAL DOCUMENT

## Purpose

David has approved the project. Before we kick off, I need your input on internal resourcing, team assignments, tooling, process, and a few business decisions that are on our side of the table. This document covers everything I need from you so we can hit the ground running.

Project snapshot: $30,520–$34,720 total · 316 hours (non-dev) + 120–180 hours (dev) · ~10 weeks · 6 milestone payments at $70/hr

# 1. Team & Resourcing

We have 5 overlapping workstreams running for ~10 weeks. I need to know who’s doing what and how much of their time I can count on.

| # | Question | Context / Why It Matters | Decision / Answer |
| --- | --- | --- | --- |
| 1 | Who is the lead developer for this project? Is it Irish, or someone else? | Development is 120–180 hours over Weeks 4–9. This person needs to be locked in and not pulled onto other projects mid-build. |  |
| 2 | Do we have a dedicated designer, or am I handling UX/design with AI tools (Claude Artifacts, v0.dev, Figma)? | UX + Visual Design is 118 hours combined (Weeks 2–5). If I’m doing it with AI assistance, that’s fine, but I need to plan accordingly. |  |
| 3 | Who handles SEO? Do we have someone in-house, or am I owning the 126-hour SEO workstream? | SEO is the single largest workstream. 71 individual page specs, keyword research across 4 pillars, schema markup, redirect mapping. This is not a side task. |  |
| 4 | Can Irish (or whoever is on dev) be dedicated full-time during Weeks 4–9, or will they be split across projects? | The overlapping timeline only works if dev starts as soon as homepage design is approved. Delays here cascade into everything. |  |
| 5 | Do we need QA support beyond the dev team? Or is the developer self-testing with a final QA pass from me? | SOW includes 36 hours for Testing & Launch. Cross-browser, mobile, checkout, redirect verification, performance. |  |
| 6 | If David’s content delivery is slow and we need to keep dev moving, can we bring in a copywriter to ghostwrite from his content briefs? | David is responsible for ~71 pages of content per the SOW. This is the single biggest timeline risk. I want a backup plan. |  |
| 7 | What’s our total team capacity on this project per week? How many billable hours can we realistically put toward Inc123? | At 40 hrs/week dedicated, this is a 9-week project. At 20 hrs/week shared, it’s 16+ weeks. I need a realistic number to set David’s expectations. |  |

# 2. Tools & Infrastructure

Need decisions on tooling before Discovery starts so I can set everything up.

| # | Question | Context / Why It Matters | Decision / Answer |
| --- | --- | --- | --- |
| 8 | What project management tool are we using? (Jira, Asana, Linear, Trello, something else?) | I need to build a task board from the 112-task project plan. Need to know the platform before I set it up. |  |
| 9 | What time tracking tool should we use for this project? | SOW is hourly at $70/hr with milestone-based invoicing. We need accurate time tracking per workstream to invoice correctly. |  |
| 10 | Do we have a staging environment ready, or do I need to set one up? | Dev starts Week 4. Staging needs to be ready before then. Need to know if we have a standard setup or if I’m provisioning. |  |
| 11 | What’s our standard for design deliverables? Figma, or are we comfortable with Claude Artifacts / coded prototypes? | The SOW promises clickable prototypes. I can build these as React/HTML artifacts or in Figma. Different skill requirements. |  |
| 12 | Do we have Ahrefs, SEMrush, or Screaming Frog licenses for the SEO work? | Keyword research and technical auditing require these tools. If we don’t have them, I need to budget subscriptions or find alternatives. |  |
| 13 | Git repo setup — GitHub, GitLab, or Bitbucket? Any existing BIT Studios standards? | Need version control from day one of development. Want to follow whatever our standard is. |  |
| 14 | Do we have a shared drive or folder structure for client deliverables? Or should I create one? | Strategy docs, SOW, design files, SEO specs, content briefs — all need a home. Want to keep things organized from the start. |  |

# 3. CMS & Technical Direction

The SOW leaves the CMS decision (WordPress vs. Payload CMS) for after Discovery. But internally, I want your input before I make a recommendation to David.

| # | Question | Context / Why It Matters | Decision / Answer |
| --- | --- | --- | --- |
| 15 | Do you have a preference between WordPress and Payload CMS for this project? | WordPress is safer for client self-management. Payload is more modern, headless, better DX. SOW prices dev at 120–180 hrs for either. |  |
| 16 | Does our team have Payload CMS experience, or would it be a learning curve? | If nobody’s built a Payload site before, WordPress is the pragmatic choice even if Payload is technically better. |  |
| 17 | What’s our standard hosting recommendation for WordPress clients? (WP Engine, Cloudways, SiteGround, etc.) | Need to factor hosting into the recommendation. Affects performance, SSL, deployment workflow. |  |
| 18 | The checkout flow requires Stripe/PayPal integration with order emails and basic admin tracking. Have we built similar e-commerce flows before? | This isn’t WooCommerce — it’s a custom checkout for service packages. Want to know if we have reusable patterns or if this is from scratch. |  |
| 19 | Are there any WordPress themes or starter frameworks we typically use, or do we build custom from scratch? | Custom theme is in the SOW, but starting from a starter theme (Sage, Underscores, GeneratePress) could save 10–20 dev hours. |  |

# 4. Budget, Billing & Financial

The SOW is signed at $70/hr with 6 milestone payments. Need alignment on internal tracking and margins.

| # | Question | Context / Why It Matters | Decision / Answer |
| --- | --- | --- | --- |
| 20 | How do we want to handle invoicing? Do I draft invoices for your review, or does someone else handle billing? | 6 milestone invoices over ~10 weeks. First one (~$2,520) is due at Discovery approval. Need the process clear. |  |
| 21 | Do we have a change order template, or should I create one? | SOW §7.3 requires written Change Orders for scope changes. Want a professional template ready before the first request comes in. |  |
| 22 | If David requests something clearly out of scope during the project, what’s my authority level? Can I quote change orders directly, or do they go through you? | Things will come up. Want to be responsive to David while respecting internal approval process. |  |
| 23 | The development hours are quoted as 120–180 (TBD after Discovery). What’s our internal target? Should I push toward the lower end or scope for quality? | Difference is ~$4,200 in revenue. Lower is leaner and faster but risks cutting corners. Higher gives more room for polish. |  |
| 24 | Are there any internal cost thresholds or margin targets I should be aware of? | Helps me make trade-off decisions when they come up — e.g., buying a premium plugin vs. building custom. |  |
| 25 | Is there budget for third-party tools or licenses if needed? (Stock photography, premium WordPress plugins, SEO tools, etc.) | Some tools might be needed. Want to know if I can expense them or if they come out of project margin. |  |

# 5. Client Communication & Management

David is hands-on and detail-oriented. He values expertise and thorough explanations. I want to make sure we’re aligned on how to manage him.

| # | Question | Context / Why It Matters | Decision / Answer |
| --- | --- | --- | --- |
| 26 | Do you want to be on the kickoff call with David, or should I run it solo? | You were on the initial meetings. Want to know your involvement level going forward. |  |
| 27 | What level of visibility do you want into the project? (Attend client meetings, CC on emails, weekly internal update, etc.) | I’ll manage day-to-day. Want to make sure you’re in the loop at the right level without creating overhead. |  |
| 28 | If David pushes back on a design or strategic decision, what’s our stance? Client is always right, or do we push back with rationale? | David has strong opinions and deep industry knowledge. Sometimes he’ll know better than us. Sometimes our expertise should win. Want alignment. |  |
| 29 | How should I handle it if David’s content delivery falls significantly behind schedule? | Content is 100% his responsibility per the SOW. But if it delays dev, we’re sitting idle. Do we formally notify, offer to help (at extra cost), or just wait? |  |
| 30 | The SOW includes 2 revision rounds per workstream. If David consistently pushes for a third round, how aggressive should I be about enforcing the limit vs. absorbing it? | Depends on client relationship strategy. Strict enforcement protects margin but can damage the relationship. |  |

# 6. Risk Management & Escalation

Things that could go sideways and how we should handle them.

| # | Question | Context / Why It Matters | Decision / Answer |
| --- | --- | --- | --- |
| 31 | If the project starts running over hours on a workstream, at what point do I escalate to you? | Want a threshold. 10% over? 20%? Or just flag it as it happens? |  |
| 32 | David’s current site has been running for 25 years. Are there any technical risks you foresee with the migration we should plan for? | Legacy hosting, old DNS configs, email routing tied to the domain — things that could blow up during launch if we’re not careful. |  |
| 33 | What’s our contingency if the developer gets pulled to another project or leaves mid-build? | 120–180 dev hours is 3–4 weeks of full-time work. If we lose the dev, we need a plan. |  |
| 34 | Should we consider a phased launch (core pages first, remaining pages in a second release)? | Reduces launch risk. Get homepage + pillar pages + package pages live, then add cluster pages and remaining content in a follow-up. |  |
| 35 | The 30-day warranty (SOW §11) — how do we want to handle warranty requests? Separate task queue, or just absorb into normal workflow? | Need a process so warranty work doesn’t get lost or deprioritized. |  |

# 7. Post-Launch & Growth Opportunities

The SOW explicitly lists several out-of-scope items that are natural upsell opportunities. Want your read on how aggressively to plant these seeds.

| # | Question | Context / Why It Matters | Decision / Answer |
| --- | --- | --- | --- |
| 36 | Do we want to pitch ongoing SEO as a retainer once the site launches? ($1,500–$3,000/month was in our estimates.) | The SEO foundation we’re building is designed to be maintained. Without ongoing work, rankings will stagnate. |  |
| 37 | Content marketing retainer — should I position this during the project, or wait until after launch? | David will have seen the value of content strategy by launch. Monthly blog posts, landing pages, case studies are natural next steps. |  |
| 38 | Maintenance & support agreement — do we have a standard template, or should I draft one specific to this project? | WordPress sites need updates, security monitoring, backups. $500–$1,500/month was in our estimates. |  |
| 39 | The SOW lists advanced features as out of scope (interactive calculator, client portal, shelf company inventory system). Should I note these as “future phases” during the project? | Planting seeds now makes the upsell easier later. But don’t want to distract David from current scope. |  |
| 40 | Is there a BIT Studios portfolio case study opportunity here? The SOW gives us the right to display the project with David’s approval. | 25-year-old company, privacy niche, full redesign with pillar/cluster SEO strategy — strong case study material. |  |

## Summary of What I Need From You

The most time-sensitive items are team assignments (#1–7), tooling decisions (#8–14), and your involvement level (#26–27). Everything else can be discussed as we go, but ideally I’d like answers on all 40 before we kick off with David.

Once I have your input, I’ll finalize the internal project setup, build the task board, and schedule the client kickoff.

BIT Studios  ·  INTERNAL  ·  Incorporate123 Project  ·  40 Questions for Jeff