## Dashboard
DISCOVERY PHASE DASHBOARD
TIMELINE
PROJECT METRICS |  | Discovery & Strategy | Weeks 1-2 (36 hrs)
Total Current URLs | ~171 | UX & Design | Weeks 2-5
Unique Content Pages | ~129 | SEO Strategy | Weeks 3-8
Duplicate/Redundant URLs | ~42 | Development | Weeks 4-9
Learning Center FAQ Items | ~111 | Testing & Launch | Weeks 8-10
Target New Pages | 71+
301 Redirects Required | ~170
Current Template Types | 15
New Template Types | 8-10
PILLAR BREAKDOWN
Privacy (Lead Pillar) | 11
Asset Protection | 7
Formation | 9
Compliance | 7
Package Pages | 8
State Hubs | 4
Utility & Support | 9+
DISCOVERY DELIVERABLES
Current site audit | Not Started
Content mapping | Not Started
Competitive analysis | Not Started
User journey mapping | Not Started
Discovery report | Not Started
Redirect planning | Not Started
Stakeholder alignment | Not Started

## Current Site Audit
INCORPORATE123 — CURRENT SITE AUDIT
Phase 1: Discovery & Strategy · ~171 URLs to catalog · Weeks 1–2
ID | Current URL | Page Title | Page Type | Template Type | Word Count (est.) | Has Unique Content? | SEO: Title Tag | SEO: Meta Description | SEO: H1 | Traffic (if known) | Backlinks (if known) | Content Quality | Action | New Destination URL | Redirect Type | Notes
MAIN NAVIGATION PAGES
1 | / | Home | Landing | Homepage
2 | /services/compare-order/ | Compare & Order Packages | Package | Compare/Order
NEVADA PAGES
3 | /services/nevada-llc/ | Nevada LLC | Service | Service Detail
4 | /services/nevada-corporation/ | Nevada Corporation | Service | Service Detail
5 | /services/nevada/bronze-llc/ | Nevada Bronze LLC ($1,000) | Package | Package/Pricing
6 | /services/nevada/bronze-corp/ | Nevada Bronze Corp ($1,300) | Package | Package/Pricing
7 | /services/nevada/silver-basic-llc/ | Nevada Silver Basic LLC ($1,275) | Package | Package/Pricing
8 | /services/nevada/silver-basic-corp/ | Nevada Silver Basic Corp ($1,575) | Package | Package/Pricing
9 | /services/nevada/silver-exec-llc/ | Nevada Silver Exec LLC ($1,575) | Package | Package/Pricing
10 | /services/nevada/silver-exec-corp/ | Nevada Silver Exec Corp ($1,875) | Package | Package/Pricing
11 | /services/nevada/gold-basic-llc/ | Nevada Gold Basic LLC ($1,800) | Package | Package/Pricing
12 | /services/nevada/gold-basic-corp/ | Nevada Gold Basic Corp ($2,100) | Package | Package/Pricing
13 | /services/nevada/gold-exec-llc/ | Nevada Gold Exec LLC ($2,100) | Package | Package/Pricing
14 | /services/nevada/gold-exec-corp/ | Nevada Gold Exec Corp ($2,400) | Package | Package/Pricing
WYOMING PAGES
15 | /services/wyoming-llc/ | Wyoming LLC | Service | Service Detail
16 | /services/wyoming-corporation/ | Wyoming Corporation | Service | Service Detail
17 | /services/wyoming/silver-llc/ | Wyoming Silver LLC ($900) | Package | Package/Pricing
18 | /services/wyoming/gold-llc/ | Wyoming Gold (Private) LLC ($1,275) | Package | Package/Pricing
19 | /services/wyoming/gold-virtual-office/ | Wyoming Gold + Virtual Office ($1,675) | Package | Package/Pricing
CALIFORNIA & FLORIDA PRIVATE PAGES
20 | /services/california/ | California Private Company | Service | Service Detail
21 | /services/florida/ | Florida Private Company | Service | Service Detail
SHELF COMPANIES
22 | /services/shelf-companies/ | Shelf Companies Overview | Service | Service Detail
VIRTUAL OFFICE
23 | /services/virtual-office/ | Virtual Office Services | Service | Service Detail
OFFSHORE / INTERNATIONAL PAGES
24 | /offshore/nevis-llc/ | Nevis LLC ($2,060) | Offshore | Offshore
25 | /offshore/nevis-corp/ | Nevis Corporation ($2,290) | Offshore | Offshore
26 | /offshore/bvi/ | BVI Company ($3,200) | Offshore | Offshore
27 | /offshore/panama/ | Panama Foundation | Offshore | Offshore
28 | /offshore/bahamas/ | Bahamas Dynasty Trust | Offshore | Offshore
29 | /offshore/hong-kong/ | Hong Kong Company | Offshore | Offshore
ADD-ON SERVICES
30 | /services/add-on-services/ | Add-on Services | Service | Service Detail
31 | /services/registered-agent/ | Registered Agent Services | Service | Service Detail
LEARNING CENTER / EDUCATIONAL CONTENT (~111 FAQ items)
32 | /learning-center/ | Learning Center Index | Educational/FAQ | Category Index
33 | /learning-center/nevada/ | Learning: Nevada | Educational/FAQ | Category Index
34 | /learning-center/wyoming/ | Learning: Wyoming | Educational/FAQ | Category Index
35 | /learning-center/privacy/ | Learning: Privacy | Educational/FAQ | Category Index
36 | /learning-center/asset-protection/ | Learning: Asset Protection | Educational/FAQ | Category Index
37 | /learning-center/llc-basics/ | Learning: LLC Basics | Educational/FAQ | Category Index
38 | /learning-center/corporations/ | Learning: Corporations | Educational/FAQ | Category Index
FAQ ITEMS (expand as crawled — ~111 items across overlapping paths)
UTILITY & SUPPORT PAGES
39 | /about-us/ | About Us | Utility | About/Legal
40 | /contact/ | Contact | Utility | Contact/Form
41 | /about-us/privacy/ | Privacy Policy | Utility | About/Legal
42 | /site-map/ | Site Map | Utility | Site Map
43 | /billing/ | Billing / Client Login | Utility | Checkout
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173

## New Architecture
INCORPORATE123 — NEW SITE ARCHITECTURE (71+ Pages)
ID | Pillar | Page Name | Page Type | New URL | Template Type | Content Sources (old pages) | Primary Keywords | Internal Links To | Schema Type | Priority | Status
PILLAR 1: BUSINESS PRIVACY (Lead Pillar) — 11 pages
1 | Privacy | Business Privacy | Pillar | /privacy/ | Pillar Page | NV/WY privacy content scattered | business privacy, private LLC, anonymous company | All privacy clusters, comparison pages, packages | Organization, Service | P1 - Critical | Not Started
2 | Privacy | Anonymous LLC | Cluster | /anonymous-llc/ | Cluster Page | Gold package privacy content | anonymous LLC, form LLC anonymously | → Privacy pillar, Nominee Services, WY Privacy, Best State | Service, FAQ | P1 - Critical | Not Started
3 | Privacy | Anonymous Corporation | Cluster | /anonymous-corporation/ | Cluster Page | Corp privacy content | anonymous corporation, private corporation | → Privacy pillar, NV Privacy, Nominee Services | Service, FAQ | P2 - High | Not Started
4 | Privacy | Nominee Services | Cluster | /nominee-services/ | Cluster Page | Scattered nominee info | nominee services, nominee director, nominee officer | → Privacy pillar, Anonymous LLC, packages | Service, FAQ, HowTo | P1 - Critical | Not Started
5 | Privacy | Wyoming Privacy | Cluster | /wyoming-privacy/ | Cluster Page | WY LLC/Corp pages | Wyoming privacy, Wyoming anonymous LLC | → Privacy pillar, WY packages, WY vs NV | Service, FAQ | P1 - Critical | Not Started
6 | Privacy | Nevada Privacy | Cluster | /nevada-privacy/ | Cluster Page | NV Gold packages | Nevada privacy, Nevada anonymous LLC | → Privacy pillar, NV packages, WY vs NV | Service, FAQ | P2 - High | Not Started
7 | Privacy | California Private Inc. | Cluster | /california-private-incorporation/ | Cluster Page | CA private page | California private company, CA anonymous LLC | → Privacy pillar, CA package, CA hub | Service, FAQ | P1 - Critical | Not Started
8 | Privacy | Florida Private Inc. | Cluster | /florida-private-incorporation/ | Cluster Page | FL private page | Florida private company, FL anonymous LLC | → Privacy pillar, FL package, FL hub | P1 - Critical |  | Not Started
9 | Privacy | BOI Reporting | Cluster | /beneficial-ownership-reporting/ | Cluster Page | NEW — no existing content | beneficial ownership reporting, BOI, corporate transparency act | → Privacy pillar, Nominee Services | FAQ, HowTo | P2 - High | Not Started
10 | Privacy | Best State for Privacy | Comparison | /best-state-for-privacy/ | Comparison Page | NEW — scattered comparisons | best state for privacy, most private state for LLC | → Privacy pillar, WY vs NV, packages | FAQ | P1 - Critical | Not Started
11 | Privacy | WY vs NV for Privacy | Comparison | /wyoming-vs-nevada-privacy/ | Comparison Page | NV vs WY content | Wyoming vs Nevada privacy, WY vs NV LLC | → Privacy pillar, Best State, WY/NV packages | FAQ | P1 - Critical | Not Started
PILLAR 2: ASSET PROTECTION — 7 pages
12 | Asset Protection | Asset Protection | Pillar | /asset-protection/ | Pillar Page | AP content from NV pages | asset protection LLC, protect assets from lawsuits | All AP clusters, comparison, packages | Organization, Service | P1 - Critical | Not Started
13 | Asset Protection | Nevada Asset Protection | Cluster | /nevada-asset-protection/ | Cluster Page | NV LLC AP content | Nevada asset protection, Nevada charging order | → AP pillar, NV packages, NV vs WY AP | Service, FAQ | P2 - High | Not Started
14 | Asset Protection | Wyoming Asset Protection | Cluster | /wyoming-asset-protection/ | Cluster Page | WY LLC AP content | Wyoming asset protection, Wyoming charging order | → AP pillar, WY packages, NV vs WY AP | Service, FAQ | P2 - High | Not Started
15 | Asset Protection | Holding Company LLC | Cluster | /holding-company-llc/ | Cluster Page | NEW — enhance from existing | holding company LLC, investment holding LLC | → AP pillar, packages | Service, FAQ | P2 - High | Not Started
16 | Asset Protection | Real Estate AP | Cluster | /real-estate-asset-protection/ | Cluster Page | NEW | real estate asset protection, rental property LLC | → AP pillar, Holding Co, packages | Service, FAQ | P3 - Medium | Not Started
17 | Asset Protection | NV vs WY for AP | Comparison | /nevada-vs-wyoming-asset-protection/ | Comparison Page | Scattered comparisons | Nevada vs Wyoming asset protection | → AP pillar, NV AP, WY AP, packages | FAQ | P2 - High | Not Started
18 | Asset Protection | Best State for AP | Comparison | /best-state-for-asset-protection/ | Comparison Page | NEW | best state for asset protection | → AP pillar, NV vs WY AP | FAQ | P2 - High | Not Started
PILLAR 3: COMPANY FORMATION — 9 pages
19 | Formation | Company Formation | Pillar | /company-formation/ | Pillar Page | Main service pages | LLC formation, incorporate, start a business | All formation clusters, comparison, packages | Organization, Service | P1 - Critical | Not Started
20 | Formation | Wyoming LLC | Cluster | /wyoming-llc/ | Cluster Page | WY LLC page | Wyoming LLC, form LLC in Wyoming | → Formation pillar, WY packages, WY hub | Service, FAQ | P1 - Critical | Not Started
21 | Formation | Wyoming Corporation | Cluster | /wyoming-corporation/ | Cluster Page | WY Corp page | Wyoming corporation, incorporate in Wyoming | → Formation pillar, WY packages | Service, FAQ | P3 - Medium | Not Started
22 | Formation | Nevada LLC | Cluster | /nevada-llc/ | Cluster Page | NV LLC page | Nevada LLC, form LLC in Nevada | → Formation pillar, NV packages, NV hub | Service, FAQ | P1 - Critical | Not Started
23 | Formation | Nevada Corporation | Cluster | /nevada-corporation/ | Cluster Page | NV Corp page | Nevada corporation, incorporate in Nevada | → Formation pillar, NV packages | Service, FAQ | P3 - Medium | Not Started
24 | Formation | LLC vs Corporation | Comparison | /llc-vs-corporation/ | Comparison Page | Learning center content | LLC vs corporation, LLC or corp | → Formation pillar, state clusters | FAQ | P2 - High | Not Started
25 | Formation | Wyoming vs Nevada | Comparison | /wyoming-vs-nevada/ | Comparison Page | Existing comparison content | Wyoming vs Nevada LLC, WY vs NV | → Formation pillar, state clusters, packages | FAQ | P1 - Critical | Not Started
26 | Formation | Shelf Companies | Cluster | /shelf-companies/ | Cluster Page | Shelf company page | shelf company, aged LLC, aged corporation | → Formation pillar, packages | Product | P3 - Medium | Not Started
27 | Formation | Offshore Entities | Cluster | /offshore/ | Cluster Page | All offshore pages | offshore LLC, Nevis LLC, BVI company | → Formation pillar | Service | P4 - Low | Not Started
PILLAR 4: COMPLIANCE — 7 pages
28 | Compliance | Compliance | Pillar | /compliance/ | Pillar Page | RA + compliance content | business compliance, annual report, registered agent | All compliance clusters, packages | Organization, Service | P2 - High | Not Started
29 | Compliance | Registered Agent Services | Cluster | /registered-agent/ | Cluster Page | RA page | registered agent, statutory agent | → Compliance pillar, packages | Service, FAQ | P2 - High | Not Started
30 | Compliance | Annual Reports | Cluster | /annual-reports/ | Cluster Page | Learning center content | annual report filing, state annual report | → Compliance pillar, RA | Service, HowTo | P3 - Medium | Not Started
31 | Compliance | Foreign Registration | Cluster | /foreign-registration/ | Cluster Page | CA/FL registration info | foreign registration, register LLC in another state | → Compliance pillar, CA/FL packages | Service, HowTo | P3 - Medium | Not Started
32 | Compliance | Domestication | Cluster | /domestication/ | Cluster Page | Limited existing content | domestication, move LLC to another state | → Compliance pillar | Service, HowTo | P3 - Medium | Not Started
33 | Compliance | Corporate Minutes | Cluster | /corporate-minutes/ | Cluster Page | Nominee/compliance content | corporate minutes, annual minutes | → Compliance pillar, Nominee Services | Service | P3 - Medium | Not Started
34 | Compliance | Virtual Office | Cluster | /virtual-office/ | Cluster Page | Virtual office page | virtual office, business address | → Compliance pillar, packages | Service | P3 - Medium | Not Started
PACKAGE PAGES — 8 pages
35 | Packages | Wyoming Gold (Private) | Package | /wyoming-private-incorporation/ | Package Page | WY Gold packages | Wyoming private incorporation, anonymous Wyoming LLC | → Privacy pillar, WY clusters, checkout | Product, FAQ | P1 - Critical | Not Started
36 | Packages | Wyoming Silver | Package | /wyoming-incorporation/ | Package Page | WY Silver package | Wyoming incorporation, form Wyoming LLC | → Formation pillar, WY clusters, checkout | Product, FAQ | P1 - Critical | Not Started
37 | Packages | Nevada Gold (Private) | Package | /nevada-private-incorporation/ | Package Page | NV Gold packages | Nevada private incorporation, anonymous Nevada LLC | → Privacy pillar, NV clusters, checkout | Product, FAQ | P1 - Critical | Not Started
38 | Packages | Nevada Silver | Package | /nevada-incorporation/ | Package Page | NV Silver packages | Nevada incorporation, form Nevada LLC | → Formation pillar, NV clusters, checkout | Product, FAQ | P1 - Critical | Not Started
39 | Packages | Nevada Bronze | Package | /nevada-basic-incorporation/ | Package Page | NV Bronze packages | basic Nevada incorporation, cheap Nevada LLC | → Formation pillar, NV clusters, checkout | Product, FAQ | P2 - High | Not Started
40 | Packages | California Private | Package | /california-private-incorporation/ | Package Page | CA private page | California private company, anonymous California LLC | → Privacy pillar, CA cluster, checkout | Product, FAQ | P1 - Critical | Not Started
41 | Packages | Florida Private | Package | /florida-private-incorporation/ | Package Page | FL private page | Florida private company, anonymous Florida LLC | → Privacy pillar, FL cluster, checkout | Product, FAQ | P1 - Critical | Not Started
42 | Packages | Shelf Companies | Package | /shelf-companies/ | Package Page | Shelf company page | shelf company for sale, aged LLC | → Formation pillar, checkout | Product | P3 - Medium | Not Started
STATE HUB PAGES — 4 pages
43 | State Hub | Wyoming Hub | State Hub | /wyoming/ | State Hub | All WY content | Wyoming business, Wyoming LLC | All WY content across all pillars | BreadcrumbList | P2 - High | Not Started
44 | State Hub | Nevada Hub | State Hub | /nevada/ | State Hub | All NV content | Nevada business, Nevada LLC | All NV content across all pillars | BreadcrumbList | P2 - High | Not Started
45 | State Hub | California Hub | State Hub | /california/ | State Hub | CA content | California business, California LLC | CA private, compliance | BreadcrumbList | P2 - High | Not Started
46 | State Hub | Florida Hub | State Hub | /florida/ | State Hub | FL content | Florida business, Florida LLC | FL private, compliance | BreadcrumbList | P2 - High | Not Started
UTILITY & SUPPORT PAGES — 9+ pages
47 | Utility | Homepage | Homepage | / | Homepage | Current homepage | incorporate123, business formation, private incorporation | All 4 pillar pages, direct package links | Organization | P1 - Critical | Not Started
48 | Utility | About Us | Utility | /about/ | Utility | About Us page |  | Contact, testimonials | Organization | P2 - High | Not Started
49 | Utility | Contact | Utility | /contact/ | Utility | Contact page |  | About, packages | Organization | P2 - High | Not Started
50 | Utility | FAQ | Utility | /faq/ | Utility | ~111 Learning Center items |  | Pillar pages, packages | FAQ | P2 - High | Not Started
51 | Utility | Blog | Utility | /blog/ | Utility | Learning Center |  | Pillar pages |  | P3 - Medium | Not Started
52 | Utility | Testimonials | Utility | /testimonials/ | Utility | Scattered testimonials |  | About, packages |  | P3 - Medium | Not Started
53 | Utility | Client Login | Utility | /login/ | Utility | Billing page |  |  |  | P3 - Medium | Not Started
54 | Utility | Privacy Policy | Legal | /privacy-policy/ | Utility | Privacy policy |  |  |  | P4 - Low | Not Started
55 | Utility | Terms of Service | Legal | /terms/ | Utility | NEW or existing |  |  |  | P4 - Low | Not Started
56 | Utility | Offshore (de-emphasized) | Utility | /offshore/ | Utility | All offshore pages | offshore LLC, Nevis LLC | Formation pillar |  | P4 - Low | Not Started

## Content Mapping
INCORPORATE123 — CONTENT MAPPING & 301 REDIRECT PLAN
~170 URLs must be mapped · Every old URL gets a 301 redirect to its new destination
Old URL | Old Page Title | Old Page Type | Action | New Destination URL | New Page Name | Redirect Type | Content Notes | SEO Notes